- SUMMARY OF THE ACTOR´S role WITHIN THE CZECH DEVELOPMENT COOPERATION – RESPONSIBILITY MATRIX

| Responsibility Assignment Matrix of the bilateral programmes within the Czech development cooperation |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Embassy | CzDA | MFA/DCD | MFA/ TD | Partner institutions | Implementer | CDC | Public |
| Programming phase |  |  |  |  |  |  |  |  |
| Selection of the priority countries | P | P | D/P | C | I | I | C | I |
| Preparation of the cooperation programmes | C | C | P/D | C | C | C | C | I |
| Approval of the programme | C | C | D | P/C | I | I | C | I |
| Project preparation phase |  |  |  |  |  |  |  |  |
| Gathering and transfer of the project proposals | D | C | C | C | P | P | C | - |
| Preparation of the materials for the project proposals | C | D | C | C | - | - | - | - |
| Assessment of the project proposals | C | A | D | A | I | I | C | - |
| Decisions on the instruments and the form of financing | C | P | D | C | I | - | I | - |
| Preparation of a project document - public procurement | C | D | I | - | C | - | - | - |
| Preparation of a project document – subsidy (subsidy call) | C | D | I | - | I | P | I | I |
| Preparation of a project document – budgetary measure | C | D | C | - | C | P | I | - |
| Preparation of a project document - cooperation with entities from partner countries | C | D | C | - | C | P | - | - |
| Announcement and ongoing selection procedure | I | D | C | I | I | I | I | I |
| Realization phase |  |  |  |  |  |  |  |  |
| Conclusion of a contract/issue of the decision about granting a subsidy | I | D | I | - | I | C | I | I |
| Initiation of the implementation | I | D | I | I | I | P | I | I |
| Ongoing progress of the project and its implementation | C | D | C | I | C | P | I | - |
| Changes within the project | C | D | C | I | P/C | P | I | - |
| Termination of the project | C | D | C | I | P/C | P | I | I |
| Monitoring and evaluation phase |  |  |  |  |  |  |  |  |
| Internal monitoring | I | C/A | I | - | I/D | D | - | - |
| External monitoring | P/C | D/P | P/C | C | C | C | I | I |
| Evaluation | C | P | D/P | C | C | C | C | I |

D = decision-making power (actor who decides on the procedures at a given stage of the programme cycle, approves their funding and is responsible for their effective and efficient implementation)

P = initiator of the proposal (actor who submits a proposal or initiative on his own or at the discretion of the decision-making actor)

A = assessment power (actor who assesses, evaluates proposals on his own or at the discretion of the decision-making actor)

C = for consultation (actor who is consulted and can give an opinion on the decision-making actor´s appeal)

I = for information (actor who is informed by decision-making actor)

"-" = actor who is not involved in the process at this stage

„/“ = actor with more than one role

CzDA = Czech Development Agency

DCD = Development Cooperation Department of MFA

TD = Territorial Department of MFA

CDC = Council for development Cooperation

| Responsibility Matrix within the other tools of the Czech development cooperation |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Embassy | Responsible authority | MFA/DCD | MFA/ TD/CzDA | CDC | Implementer | Public |
| Programming phase |  |  |  |  |  |  |  |
| Preparation of the programme | C | P/D | C | C | C | I | I |
| Approval of the programme | C | C | D | C | C | I | I |
| Project preparation phase |  |  |  |  |  |  |  |
| Identification of the project proposals | P | D | C | C | C | P | - |
| Announcement and ongoing tender/call, etc. | I | D | C | I | I | I | I |
| Conclusion of a contract/issue of the decision about granting a subsidy | I | D | I | - | I | C | I |
| Realization phase |  |  |  |  |  |  |  |
| Initiation of the implementation | I | D | I | I | I | P | I |
| Ongoing progress of the project and its implementation | C | D | C | I | I | P | - |
| Changes within the project | C | D | C | I | I | P | - |
| Termination of the project | C | D | C | I | I | P | I |
| Monitoring and evaluation phase |  |  |  |  |  |  |  |
| Internal monitoring | I | C/A | I | - | - | D | - |
| External monitoring | P/C | D/P | C | C | I | C | I |
| Evaluation | C | P | D/P | C | C | C | I |

D = decision-making power (actor who decides on the procedures at a given stage of the programme cycle, approves their funding and is responsible for their effective and efficient implementation)

P = initiator of the proposal (actor who submits a proposal or initiative on his own or at the discretion of the decision-making actor)

A = assessment power (actor who assesses, evaluates proposals on his own or at the discretion of the decision-making actor)

C = for consultation (actor who is consulted and can give an opinion on the decision-making actor´s appeal)

I = for information (actor who is informed by decision-making actor)

"-" = actor who is not involved in the process at this stage

„/“ = actor with more than one role

DCD = Development Cooperation Department of MFA

TD = Territorial Department of MFA

CzDA = Czech Development Agency

CDC = Council for development cooperation