|  | Ministerstvo zahraničních věcí České republiky | Ministry of Foreign Affairs of the Czech Republic |
| --- | --- | --- |

THE Ministry of Foreign Affairs of the Czech Republic

CALLS FOR BIDS

FOR A SMALL-SCALE public CONTRACT

“evaluation of the czech republic development cooperation Project in the SECTOR OF AGRICULTURE AND RURAL DEVELOPMENT in ZAMBIA”

information ABOUT the CONTRACTING AUTHORITY

Name:			Ministry of Foreign Affairs of the Czech Republic

Corporate ID:		45769851

Tax ID:			CZ45769851

Registered office:	Loretánské náměstí č. 101/5, Praha 1, PSČ 118 00, Czech Republic

The Contracting Authority´s representative competent to decide on matters of substance related to the contract: Václav Bálek, Director, Development Cooperation and Humanitarian Aid Department, MFA

Official responsible of the contract award procedure: Dana Zázvorková, Development Cooperation and Humanitarian Aid Department, MFA

E-mail contact: dana_zazvorkova@mzv.cz and e-mail: ors_sekretariat@mzv.cz

tel.: +420 224 182 157 or tel.: +420 224 182 366

Description of the public contract (CPV code 79998000-6 Coaching services)

The aim is to evaluate 1 (one) project of the Czech Republic development cooperation implemented in Zambia under the auspices of the Czech Development Agency (“CzDA”) in 2014–2018. The evaluation outputs can be used in thematic areas of agriculture and rural development.

The evaluation will take place from February to October 2020.

The conclusions and recommendations will be highly relevant for the overall direction of development activities in the thematic area of agriculture and rural development, which is the main priority of the Czech Bilateral Development Cooperation Program with Zambia for the years 2018–2023.

Evaluations of the Czech development cooperation programs and projects are based on the Act No. 151/2010 Sb., on Development Cooperation and Humanitarian Aid, the Development Cooperation Strategy of the Czech Republic 2010 – 2017, the Development Cooperation Strategy of the Czech Republic 2018 – 2030, the applicable provisions of the Project Cycle Methodology for Bilateral Development Cooperation Projects and relevant Zambia strategy documents.

Evaluation shall be performed in accordance with the internationally recognised OECD-DAC criteria and with other specified evaluation criteria (visibility and cross-cutting principles of the Czech development cooperation) assessing long-term impacts and sustainability of the projects.

Conclusions and recommendations will be highly relevant for further direction and financing of Czech development cooperation in Zambia and also for the implementation of similar projects in the sector of agriculture and rural development.

The project will be evaluated:

“Appropriate and stable fodder production for dairy cattle in the small scale farms”

| Remit: | Czech Development Agency |
| --- | --- |
| Sector: | Agriculture and rural development |
| Implementation period: | 2014–2018 |
| Project type: | Public procurement |
| Implementer: | Mendel University in Brno |
| Local partner/implementer: | Choma District Dairy Cooperative Monze Dairy Cooperative Ministry of Agriculture and Livestock Golden Valley Agricultural Research Trust and Czech partners Njovu o.p.s. a Geotest s.r.o. |
| Expenditure in CZK: | 15.9 million CZK |
| Identification number of project: | CzDA-ZM-2014-9-31195 |

Principal stakeholders

Ministry of Foreign Affairs of the Czech Republic (“MFA”) is responsible for development cooperation of Czech Republic management at conceptual and bilateral level, including results evaluation. Development Cooperation and Humanitarian Aid Department of the MFA cooperates with MFA territorial departments, Embassies of the Czech Republic and Czech Development Agency (“CzDA”).

Embassy of the Czech Republic in Lusaka represents the Czech Republic in Zambia as to the development cooperation, a relevant member of the diplomatic staff is in charge of development cooperation coordination and monitoring tasks.

Czech Development Agency (“CzDA”) has been active since 1st January 2008 as an implementation agency of the Czech Republic development cooperation, in particular of bilateral development projects´ preparation, implementation and monitoring. Selection and implementation of the projects and grant programs is based on the partner countries requirements and in accordance with the MFA.

Implementers

Mendel University implemented the evaluated project in the form of a public procurement based on a contract with the Czech Development Agency in 2014–2018.

Reference group

Together with the contracting authority, the evaluation process will be supervised by an expert reference group consisting of representatives of the MFA - Development Cooperation and Humanitarian Aid Department, Czech Development Agency, MFA – Department of Sub-Saharan Africa (“AFR”), the Ministry of Agriculture (“MZe”) and the independent expert of the Czech Evaluation Society (“ČES”).

Communication between the evaluation team and the contractor will be provided by an authorized representative of the Ministry of Foreign Affairs. The members of the expert reference group shall have the right, while preserving the impartiality, to comment on the reports submitted by the contractor.

Detailed information on the project

The aim of the project was to ensure stable and sustainable production of dairy cattle in the small scale farms.

The direct target group is represented by two cooperatives of farmers in Choma and Monza.

The long-term goal is to contribute to increasing the incomes of small scale dairy farmers.

Main outcomes included:

• Increased feed production capacity
• Sustainable use of agricultural technology for fodder production
• Introduced Holistic soil and animal management in 1 community in each area
• Providing a water source for farm animals

Purpose of the evaluation and further use of results

The main purpose of evaluations is to obtain independent, objective and consistent findings, conclusions and recommendations valuable for making decisions by MFA, in cooperation with Czech Development Agency, about the future orientation and implementation of the Czech Republic development cooperation in Zambia considering the 2030 Agenda for Sustainable Development and the Development Cooperation Strategy of the Czech Republic 2018 – 2030.

Evaluation shall be performed in accordance with the internationally recognised OECD-DAC criteria, i.e. relevance, coherence, efficiency, effectiveness, impact and sustainability, and other criteria (visibility and crosscutting themes of the Czech development cooperation).

An important aim of the contracting authority is to obtain an independent evaluation of processes and procedures associated with the implementation of the evaluated type of projects with an emphasis on its efficiency and effectiveness.

Principal evaluation questions:

Relevance

- To what extent is the project relevant to the strategic objectives of Zambia, the Czech development cooperation and the involved individual actors?

- Are the project implementation criteria appropriately set?

Coherence

- To what extent have the activities been coordinated with the activities of other donors?

- Which possibilities of cooperation with other donors do the project outputs offer?

Efficiency

- How can be evaluated (on the basis of the available information) the cost-effectiveness of the projects, in particular in terms of overall “value for money”?

- What are the main factors contributing to the in/effectiveness of project in terms of both process and content?

Effectiveness

- To what extent have the planned project outputs been achieved?

- To what extent does the project help increase the incomes of small scale dairy farmers in Zambia?

- To what extent does the project lead to increased feed production capacities?

Impacts

- What are the main development impacts of the projects?

Sustainability

- Which project parameters are crucial for its sustainability?

Additional evaluation criteria

Evaluation will assess the project also as to visibility and as to the implementation of the crosscutting themes of the Czech development cooperation defined in the Development Cooperation Strategy of the Czech Republic 2018 – 2030: good (democratic) governance; environment (sustainable development); human rights, including gender equality.

Evaluators should, in particular, assess whether and how the cross-cutting principles or some of them (as applicable) were directly associated with the sector/theme of evaluated interventions; whether and how the cross-cutting principles were implemented.

Evaluation will be elaborated in compliance with the certified Methodology for Evaluation of Crosscutting Themes in the Czech Republic Development Cooperation prepared by the Institute for Evaluations and Social Analyses – INESAN within the OMEGA programme of the Technology Agency of the Czech Republic.

Recommendations based on the evaluation findings and conclusions

The final evaluation report will give specific and feasible recommendations, with added value, stating the level of importance of such recommendation and directed specifically to the MFA, the CzDA, the implementers or other relevant development cooperation partners.

Such recommendations should be adequately supported by specific findings and conclusions, arranged by the main recipient or by level of recommendation importance, with indication of suggested measures, time prospect, etc. The recommendations should be specific for each recipient because of its further arrangements - different recipients should not share the same general recommendations. Recommendations for further management of development cooperation projects or for modification of existing programs and procedures of Czech development cooperation are highly appreciated.

Required outputs, deadlines

- The contracting authority requires the submission of one input evaluation report and one final evaluation report which will subsequently be published on the MFA website. The input report, structured according to the attached mandatory outline, expands in detail on the evaluation methodology, describes the sets of evaluation questions and hypotheses formulated on the basis of a study of documents and interviews. The input report also contains the schedule of the work, including a plan of meetings, interviews, focus groups, observations, scientific measurements, surveys, etc. Draft of the input report must be submitted for comments to the expert reference group latest by 6th April 2020.

- The input report must be discussed with the contracting authority and the expert reference group and submitted both as a bound hardcopy publication and in electronic form, with comments incorporated at least 5 days prior to the team’s departure for the evaluation mission to Zambia.

- Final evaluation report structured according to the attached mandatory outline will be a maximum of 4 (four) A4 pages of executive summary and maximum 25 pages A4 (excluding annexes). Bearing in mind the stipulated scope, the contracting authority expects the final evaluation report to contain, in particular,  key points of the independent evaluation, including summary of main findings, basic information on the evaluated intervention, description of used evaluation methodology and, in particular, independent findings, conclusions and recommendations.

- Annexes will provide background data for evaluation findings and all additional information, quantitative facts, models and results of questionnaires, etc. - according to the evaluation methodology. As part of the processing of sources of verifiable findings, the evaluation team will respect the right to protect private respondents and anonymize the sources of their findings according to the Code of Ethics of the Czech Evaluation Society.

- The evaluation report shall be elaborated in Czech or Slovak (with an English summary), or, in the case of international evaluation team, in English (with Czech summary). Annexes to the evaluation report can be kept, where relevant, in the original language.

- Draft of final evaluation report in edited way, structured in accordance with the attached mandatory outline and with all annexes, must be submitted to the contracting authority for comments by 31st August 2020. The contracting authority will collect comments from the expert reference group and pass them on to the evaluation team who is required to process the content related comments (i.e. incorporate them into the report, or reject them, with reasons and in writing). The implementers and where appropriate also the implementers’ local partners of evaluated projects will be also invited to comment on the final report - the evaluation team must cope with their suggestions as well.

- The contracting authority expects the evaluation team to present main findings, conclusions and recommendations of evaluation report at a public presentation with discussion organised by the Development Cooperation and Humanitarian Aid Department of the MFA. The presented report will already reflect comments and suggestions of expert reference group, implementers and local partners. Any additional major observations arising from the presentation with discussion will be incorporated as a separate annex to the final version of the report. The date of presentation will be mutually agreed sufficiently in advance. Prior to the presentation the evaluation team shall send a visual outline of the presentation (PowerPoint) to the contracting authority for approval at least 2 days before public presentation at MFA.

- The final evaluation report must be submitted to the contracting authority by 30rd October 2020. The final evaluation report will subsequently be published on the MFA website. The final evaluation report must be delivered to the contracting authority in a hardcopy, i.e. as one bound copy and in electronic form on a CD/DVD/USB.

Evaluation mission and further instructions for bidders

- Assessment of the projects implemented in Zambia, in the form of an evaluation mission, is an obligatory part of the evaluation process. The minimum research period in the partner country is 5 working days - depending on the nature of the projects and selected methodology. Regarding the overall procurement schedule the evaluation mission is expected during the second half of May 2020. The evaluation team will specify the evaluation mission schedule upon agreement with implementers, local partners and institutions involved including the Embassy of the Czech Republic in Zambia.

- During the course of the evaluation procurement, the team will conduct interviews with representatives of the MFA, the CzDA, the Embassy of the Czech Republic in Lusaka, the implementers, representatives of recipients and partner organizations of the implementers in Zambia (including other respondents if required).

- The evaluation team should start formulating the main focus of the findings, conclusions and recommendations in writing while still on the mission in the partner country (Zambia). An opening and closing briefing for stakeholders (relevant authorities of the partner country, representatives of the recipients, local implementation partners and implementers, the Czech Embassy in Lusaka, etc.) should be organized by the team. Preliminary findings and conclusions can be so tested in discussion and relevant feedback can be obtained. The presentation or minutes from such briefings should be included as an annex to the final evaluation report. A similar briefing with the expert reference group after the mission is finished is also recommended.

- The evaluation team is also expected to hold detailed consultations with the Embassy of the Czech Republic in Lusaka. The Embassy can be contacted in advance with requests for logistical support or for interviews with local authority arrangements. Nevertheless, assistance of the Embassy should be required unless strictly necessary.

Publication of the call and receipt of bids

The public contract will be awarded through an open bidding procedure. The call for bids is published on the MFA website on 7th February 2020.

Bids shall be based on supporting documentation concerning the projects that are to be evaluated. Requests for supporting documentation shall be sent by e-mail to the organizer of the contract award procedure: dana_zazvorkova@mzv.cz and copied to email: ors_sekretariat@mzv.cz

The deadline for receipt of bids is 26th February 2020, 14:00 (CET).

Bids must be submitted by registered mail or delivered personally both in paper and electronic form on a data storage device (CD ROM or USB flash) to the Ministry of Foreign Affairs of the Czech Republic:

Ministerstvo zahraničních věcí ČR

- Odbor rozvojové spolupráce a humanitární pomoci

- Loretánské náměstí 101/5

118 00 Praha 1

Czech Republic

Bids must be submitted in a sealed envelope marked as follows:

- title of the public contract;

- bidder´s full name (or business name) and address;

- note:

veřejná zakázka – Neotevírat – ihned předAT ORS – „VYHODNOCENÍ PROJEKTU ZAJIŠTĚNÍ UDRŽITELNÉ A STABILNÍ PRODUKCE KRMIVA PRO DOJNÝ SKOT DROBNÝCH FARMÁŘŮ (ZAMBIE)“

Bids submitted through other channels (e.g. by fax or e-mail); bids delivered to another address and/or bids submitted after the deadline will be rejected.

Bid is considered as submitted by registered mail according to the date and time registered by the mailroom of the contracting authority – Ministry of Foreign Affairs.

Bid may be submitted personally on working days from Monday to Friday from 8:00 a.m. to 16:00 p.m. (CET) at the reception of the MFA building (see above).

Bid is considered as submitted at a moment of its physical takeover by responsible employee of the contracting authority. For physical delivery it is necessary to contact the respective employee in charge or his/her substitutive.

Bids may be submitted in Czech, Slovak or English languages. Bids submitted in other languages will not be accepted.

The MFA reserves the right to reject bids that do not completely meet all the requirements set out in this Call for Bids.

Bidders are not entitled to any compensation for costs associated with participation in this Call for Bids. Any issuance associated with the submission of bids shall be borne fully by the bidders at their expense. With the exception of bids submitted after the deadline, the bids will not be returned and will remain with the contracting authority as a part of the tender documentation for this public contract.

Requests for additional information concerning this public contract procedure must be delivered to e-mail contact: dana_zazvorkova@mzv.cz and copied to e-mail: ors_sekretariat@mzv.cz no later than 17th February 2020, 23:59 (CET).

Evaluation team

The evaluation may be carried out by a team of independent experts (one of them being the team leader responsible for all provided services to the MFA) or by a legal entity with the appropriate team of experts (one of them being the team responsible for communication with the MFA).

The MFA regards as reasonable evaluation team of 2-4 experts, including the main evaluator (preferably an expert on evaluation methods, with overall responsibility for entire evaluation process and reporting); expert (-s) with a focus on the animal agriculture farming and junior member (if needed).

The expert team may be complemented by other members (e.g. interpreters, surveys´ interviewers, administrators, experts involved in the evaluation or control of data, etc.).

Bids must include the following:

- Methodological approach of the evaluation team, including a work plan (detailed description of a methodology specifically proposed for the evaluation of the projects of development cooperation of the Czech Republic in Zambia);

- Composition of evaluation team, i.e. names, contacts (e-mail, phone number) and field of expertise of those who are about to participate in the evaluation, including a clear definition of their participation in the evaluation mission, or in part of the mission and including their planned roles in the evaluation reports elaboration;

- CVs of the evaluation team experts, with clear specific information on their education, skills, expertise and experience relevant to this evaluation;

- Statutory declaration on fulfilment of the qualification requirements (see below); prior to signing the contract, the bidder must be able to demonstrate fulfilment with applicable documents/certificates; in the case of foreign evaluation team the fulfilment can be proved by analogous foreign education and experience;

- Statutory declaration of independence signed by all members of the evaluation team. All persons, or members of a legal entity, must simultaneously meet all the following independence conditions. The statutory declaration of independence is signed by all persons, or a legal entity and all the participating experts in its team;

- Bid price stated both excluding and including VAT (non-VAT payers must quote the price without the VAT and state that they are non-VAT payers). The anticipated total cost of this public contract is within an indicative range of 250,000 – 400,000 CZK excl. of the VAT;

- The completed total Evaluation Budget table (see annex) – the cost budgeted in the table is binding on the bidder. Any subsistence expenses (per diems) included in the total Evaluation Budget must be broken down per person/day and their amounts must comply with the applicable Czech regulations. Bidders should note that before paying the cost of this public contract the MFA will request a statement of the costs actually incurred, broken down by the items of the total Evaluation Budget. In justified cases, and after prior approval from the MFA, the evaluation team may be allowed to transfer funds between budget items to a maximum level of 10 per cent of the total Evaluation Budget whilst maintaining the total bid price unchanged. If the total expenditure is in reality less than that budgeted in the bid submitted to the tender, the MFA will reduce the final sum payable by this difference compared to the bid price of the winning bidder. If on the other hand the actual costs are higher than those budgeted in the bid, such additional amount will not be paid by the contracting authority - MFA;

- Extract from the Commercial Register or, where applicable, Extract from the Trade Register if the bidder (entity submitting the offer) is registered, or an extract from another similar register proving expertise, legal status, specialization, etc. The extract will be presented in a plain copy and should not be older than 90 days.

- Statutory declaration of the bidder – A Statement of Truthfulness (see annex).

Qualification requirements for Evaluation Team Experts

- All evaluation team experts as specified above must be higher education graduates;

- All evaluation team experts, except for junior member/s, must have at least 4 (four) years of professional experience - as specified above;

- All evaluation team experts, except for junior member/s, must have a past record of participation in at least one comprehensive evaluation of results of a project, programme or similar intervention;

- All evaluation team experts, except for junior members, must have completed at least one training course or higher education course on evaluation or project/program cycle management or results-based management; or must have a past record of performing an evaluation as part of thesis/dissertation work at a higher education institution, provided that thesis/dissertation was successfully accomplished;

- Documented expertise of animal agriculture farming for at least one member of the evaluation team.

- Qualification requirements may also be proved by the reference of the legal entity submitting the offer or by the reference of the natural persons who will implement subject of the procurement.

Independence of evaluation team members

- None of the evaluation team members has been involved in the preparation, selection or implementation of the projects to be evaluated at any stage nor will they participate in the year of evaluation or the following year.

- None of the evaluation team members is an employee or external associate of the projects´ coordinators, nor had he been during the period of the preparation and implementation of the evaluated projects; none of the evaluation team members is an employee or external associate of the projects´ implementers, nor had he been during the period of the preparation and implementation of the evaluated projects.

- In addition to the conditions defined above, none of the evaluation team members has been involved in the implementation of projects of development cooperation of the Czech Republic in the country of the evaluated project (Zambia) in the year prior to evaluation, in the year of the evaluation, and will not be involved in such project in Zambia in the subsequent year.

Bid assessment criteria (0 to 100 scoring scale)

The main assessment criterion will be value for money.

The sub-criteria will be as follows:

- Lowest Bid Price (excluding the VAT): 0-40 points

Maximum (40) points will be awarded for the lowest Bid Price. The remaining bids will be scored as follows: /lowest bid/ x /40 points/: /bid currently under assessment/ = /points awarded to the bid under assessment/.

2.	Professional quality, relevance (specific targeting) and feasibility of the proposed evaluation methodology, including timetable, work plan and distribution of tasks within the team: 0-30 points

The highest points will be awarded for a methodology that provides a theoretical framework for the proposed methods and identifies any limitations the methods may have, and usefully combines these methods and the OECD/DAC evaluation criteria – typically in the form of evaluation questions, the method for the identification and triangulation of data, etc. Strict compliance with the outline of the evaluation reports (input and final) and logical connections between findings, conclusions and recommendations with the stipulated evaluation questions is expected.

An optimal methodology will define a timetable of work including a tentative programme of the evaluation mission to Zambia and the division of tasks and competences within the team. These procedures must be proposed realistically. The contracting authority would welcome evaluations based on the Formal Evaluation Standards of the Czech Evaluation Society. Emphasis will be placed on professional quality, the specific targeting of the proposal and the feasibility of the evaluation methodology.

3.	Expertise and previous experience of the team with evaluations of development interventions in developing or transforming countries: 0-20 points

The highest points will be awarded to an evaluation team offering optimal combined expertise in the field of evaluations of development projects and areas related to evaluated projects. “Expertise” means a combination of theoretical knowledge and professional experience. In case the team has expertise in related fields, part of the points will be awarded for the depth, breadth and transferability of such knowledge. The team’s expertise and experience in the relevant area/sector/theme will be assessed on the basis of supporting documents enclosed with the bid.

4.	Experience from development: 0-10 points

The maximum points belong to the participant whose expert team together can demonstrably offer extensive experience in the field of international cooperation, especially in the field of development cooperation or broader assistance programs, work on the conceptual or research level of development cooperation, both from working, research or similar stay with countries or international development and humanitarian organizations; development cooperation as an activity and part of foreign policy. Experience from the implementation or evaluation of international academic cooperation and mobility is an advantage.

The criteria 2 – 4 will be assessed on the basis of the bid documentation.

The highest number of points awarded for criteria 2 – 4 may be less that the maximum stated above. The points are awarded by an expert assessment board.

The bid awarded by the highest number of points summing all above mentioned criteria points and meeting all other requirements defined by this Call for Bids will be considered the most economically advantageous bid.

Assessment of bids

Bids received in time limit (as mentioned above) will be opened by a board for bids opening. The board will check each bid for compliance with formal requirements of the contract award procedure. Qualifying bids will be presented to the assessment board for assessment against the above mentioned criteria and selection of the best bid.

Once approved the result by MFA all bidders will be notified without undue delay.

Contract of Mandate

Following the result of selection of the best bid, the MFA will enter with the selected bidder into a Contract of Mandate for evaluation. The Contract will be concluded based on Section 2586 of Act No. 89/2012, the Civil Code, as amended. It will include a clause in which the parties agree that the information contained in the Contract of Mandate and any amendments thereto will not be regarded by the parties as a business secret in terms of Section 504 of Act No. 89/2012, the Civil Code as amended, and that the parties give their unconditional consent to the disclosure and/or publication of such information namely in accordance with Act No. 106/1999 concerning free access to information as amended. A checklist of the requirements related to this public contract must be included in an annex to the Contract of Mandate.

Final provisions

The MFA will not return any of the bids received on the basis of this announcement. The MFA reserves the right to change the bidding terms and conditions or to cancel the tender without giving any reason.

Annexes:

Statutory declaration of independence (mandatory part of a bid)

Statutory declaration of truthfulness (mandatory part of a bid)

Specimen of Evaluation Budget table (mandatory part of a bid)

Mandatory outline of input evaluation report

Mandatory outline of final evaluation report

https://www.mzv.cz/aid

More information on application of OECD-DAC criteria in development cooperation evaluations is available at www.oecd.org/development/evaluation. The Project Cycle Methodology for Bilateral Projects under the Czech Republic’s Development Cooperation is available at www.mzv.cz/aid.

Development Cooperation Strategy of the Czech Republic 2018 – 2030

https://www.mzv.cz/aid

https://www.mzv.cz/aid

see annex

see annex

https://www.czecheval.cz

This tender is announced pursuant to Act No. 134/2016 Coll. about Public Procurements as a small-scale public procurement with an estimated value up to 500,000 CZK, excl. VAT. The contracting authority, however, does not intend this indicative range to serve as a strict definition of either a minimum or maximum price. The bid price must cover all of the evaluation team’s costs, i.e. the time spent working in the office (document analysis, report writing, the incorporation of comments), the cost of the evaluation mission to the partner country (the remuneration of team members, airfares, local transportation, briefings, accommodation, meals, interpreting, telephone calls), the remuneration of team members for time spent on the final presentation, etc.

See Act No. 89/2012, the Civil Code (Part 6 – Public tender and selection of the best bid).